## Log
Date | Time | Project | Category | Hours | Note
2026-04-01 | 10:14:57 | Thermofisher-Monza (36940) | Chetan | 7.5 | 1. Filling of AHU Testcase for CDZ-168. 2. Finalise pilot Delivery
2026-04-15 | 10:34:05 | Thermofisher-Monza (36940) | Chetan | 3 | Reviewed CDz-169 development of Vishnu, and observed following points: 1. Correct aliasing of fresh air TT input. 2. Parameter si units, descriptions to be cross verified. 3. 2267,2268,2269 Room pressure release logic (PDV_226701A,PDV_226701B,etc) should work. 4. TIC_169_08 logic to be implemented same as other TIC objects in EM. 5. change location of TT_2269_01 near to 2269 room objects. 6. Add Fire inputs on the CDZ-169 screens from reference CDZ-168 sec. 7. Check all CM object are set to "Program Win" command.
2026-04-15 | 10:35:42 | ZT1 Time | Chetan | 2.5 | FTOptix Training
2026-04-15 | 15:38:51 | Thermofisher-Monza (36939) | Chetan | 3 | 1. Support to Hrishikesh. 2. Support to Saniya.
2026-04-13 | 15:56:52 | Thermofisher-Monza (36939) | Chetan | 3.5 | 1. Project QMS Compliance process explained to Hrishikesh. 2. Reviewed CDZ-162 Development done by Hrishikesh, and conveyed correction points.
2026-04-13 | 15:57:55 | Thermofisher-Monza (36940) | Chetan | 4.5 | 1. Reviewed CDZ-169 Development done by Vishnu, and conveyed correction points. 2. Finalised CDZ-168 Development
2026-04-13 | 15:59:22 | ZW Time | Chetan | 0.5 | Meetings
2026-04-14 | 16:00:44 | Thermofisher-Monza (36939) | Chetan | 3.5 | 1. Support for ST2_PDS Project Development.
2026-04-14 | 16:01:29 | Thermofisher-Monza (36940) | Chetan | 4 | 1. Support to Engineers for ST7B project development
2026-04-14 | 16:01:43 | ZW Time | Chetan | 1 | Meeting
2026-04-16 | 16:04:16 | Thermofisher-Monza (36939) | Chetan | 3.5 | 1. Support to team for ST2_PDS Development
2026-04-16 | 16:04:53 | Thermofisher-Monza (36940) | Chetan | 4 | 1. Support to team for ST7B Development.
2026-04-16 | 16:05:16 | ZW Time | Chetan | 1 | Meetings
2026-04-17 | 16:05:43 | Thermofisher-Monza (36939) | Chetan | 3.5 | 1. Support to team for ST2_PDS Development
2026-04-17 | 16:06:33 | Thermofisher-Monza (36940) | Chetan | 4 | 1. Support to team for ST7B Development
2026-04-17 | 16:07:28 | ZW Time | Chetan | 1 | meetings
2026-04-20 | 06:45:43 | ZH Time | Chetan | 8.5 | On Leave
2026-04-21 | 06:46:09 | ZH Time | Chetan | 8.5 | On Leave
2026-04-22 | 12:10:10 | Thermofisher-Monza (36939) | Chetan | 3.5 | 1. Review and Support for ST2_PDS Project as per Sudipta comments 2. Review and support for Alarms configuration for CDZ-162. 3. Review and support for HMI Group configurations.
2026-04-22 | 12:11:41 | Thermofisher-Monza (36940) | Chetan | 4 | 1. Review and Support for ST7B Project as per Sudipta comments 2. Review and Support for Alarms configuration for CDZ-162. 3.Review and Support for HMI Group configurations. 4. Review and Support for ACS screens developed by saniya.
2026-04-04 | 12:32:02 | ZH Time | Chetan | 8.5 | Weekly-Off
2026-04-05 | 12:32:13 | ZH Time | Chetan | 8.5 | Weekly -Off
2026-04-11 | 12:32:54 | ZH Time | Chetan | 8.5 | Weekly-Off
2026-04-12 | 12:33:41 | ZH Time | Chetan | 8.5 | Weekly-Off
2026-04-18 | 12:33:57 | ZH Time | Chetan | 8.5 | Weekly Off
2026-04-19 | 12:34:20 | ZH Time | Chetan | 8.5 | Weekly-Off
2026-04-22 | 13:13:35 | ZT4 Time | Chetan | 1 | 1. Support for ST2_PDS. 2. Support for ST7B.
2026-04-23 | 09:57:47 | Thermofisher-Monza (36939) | Chetan | 3 | 1. Technical audit of ST2_PDS.
2026-04-23 | 09:58:08 | Thermofisher-Monza (36940) | Chetan | 4.5 | 1. Technical audit of ST7B
2026-04-23 | 09:58:42 | ZT4 Time | Chetan | 1 | 1. Support for ST2_PDS. 2. Support for ST7B.
2026-04-24 | 10:09:26 | Thermofisher-Monza (36939) | Chetan | 3 | 1. Technical audit of ST2_PDS.
2026-04-24 | 10:13:46 | ZT4 Time | Chetan | 1 | 1. Support for ST2_PDS. 2. Support for ST7B.
2026-04-24 | 10:17:02 | Thermofisher-Monza (36940) | Chetan | 4.5 | 1. Technical audit of ST7B
2026-04-28 | 14:24:57 | Thermofisher-Monza (36939) | Chetan | 3 | 1. Support for ST2_PDS QMS.
2026-04-27 | 14:26:01 | Thermofisher-Monza (36940) | Chetan | 4.5 | 1. Support for ST7B- FTV screen issue with vishnu.
2026-04-28 | 14:26:32 | Thermofisher-Monza (36940) | Chetan | 4.5 | 1. Support for ST7B- FTV screen issue with vishnu.
2026-04-27 | 14:29:12 | ZT4 Time | Chetan | 1 | 1. Support for ST2_PDS. 2. Support for ST7B.
2026-04-28 | 14:29:30 | ZT4 Time | Chetan | 1 | 1. Support for ST2_PDS. 2. Support for ST7B.
2026-04-27 | 14:30:59 | Thermofisher-Monza (36939) | Chetan | 3 | 1. Support for ST2_PDS - EMS and ACS screen and logic development 2. Pilot delivery of CDZ-162
2026-04-26 | 18:31:54 | ZH Time | Chetan | 8.5 | Weekly-Off
2026-04-25 | 18:32:06 | ZH Time | Chetan | 8.5 | Weekly-Off
2026-04-29 | 15:23:37 | Thermofisher-Monza (36939) | Chetan | 3 | 1. Support for ST2_PDS
2026-04-29 | 15:23:59 | Thermofisher-Monza (36940) | Chetan | 4.5 | 1. Support for ST7B
2026-04-29 | 15:24:17 | ZT4 Time | Chetan | 1 | 1. Support for ST2_PDS. 2. Support for ST7B.
2026-04-30 | 15:24:53 | Thermofisher-Monza (36939) | Chetan | 3 | 1. Support for ST2_PDS - Modifications suggested by Roberto
2026-04-30 | 15:25:06 | Thermofisher-Monza (36940) | Chetan | 4.5 | 1. Support for ST7B - Modifications suggested by Roberto
2026-04-30 | 15:25:22 | ZT4 Time | Chetan | 1 | 1. Support for ST2_PDS. 2. Support for ST7B.
2026-05-01 | 15:26:06 | ZH Time | Chetan | 8.5 | Holiday ( Maharastra and Labor Day)
2026-05-02 | 10:08:01 | ZH Time | Chetan | 8.5 | Weekly -Off
2026-05-03 | 10:08:12 | ZH Time | Chetan | 8.5 | Weekly -Off
2026-04-02 | 11:07:32 | Thermofisher-Monza (36940) | Chetan | 7.5
2026-04-03 | 11:08:31 | Thermofisher-Monza (36940) | Chetan | 7.5 | 1. Support to sania. 2. Support to Hrishikesh. 3. Support to Vishnu
2026-04-06 | 11:09:24 | Thermofisher-Monza (36939) | Chetan | 3
2026-04-06 | 11:09:33 | Thermofisher-Monza (36940) | Chetan | 4.5
2026-04-06 | 11:09:59 | ZT4 Time | Chetan | 1
2026-04-01 | 11:10:15 | ZT4 Time | Chetan | 1
2026-04-02 | 11:10:19 | ZT4 Time | Chetan | 1
2026-04-03 | 11:10:23 | ZT4 Time | Chetan | 1
2026-04-07 | 11:11:20 | Thermofisher-Monza (36939) | Chetan | 1.5
2026-04-07 | 11:11:25 | Thermofisher-Monza (36940) | Chetan | 2
2026-04-07 | 11:11:41 | ZT1 Time | Chetan | 4 | FT Optix Training
2026-04-07 | 11:11:53 | ZT4 Time | Chetan | 1
2026-04-08 | 11:12:13 | Thermofisher-Monza (36939) | Chetan | 1.5
2026-04-08 | 11:12:19 | Thermofisher-Monza (36940) | Chetan | 2
2026-04-08 | 11:12:30 | ZT1 Time | Chetan | 4 | FT Optix Training
2026-04-08 | 11:12:38 | ZT4 Time | Chetan | 1
2026-04-09 | 11:12:55 | Thermofisher-Monza (36939) | Chetan | 2
2026-04-09 | 11:13:03 | Thermofisher-Monza (36940) | Chetan | 3.5
2026-04-09 | 11:13:51 | ZT1 Time | Chetan | 3 | FT Optix Training
2026-04-10 | 11:14:36 | Thermofisher-Monza (36939) | Chetan | 1.5
2026-04-10 | 11:14:47 | Thermofisher-Monza (36940) | Chetan | 2
2026-04-10 | 11:15:06 | ZT1 Time | Chetan | 4 | FT Optix Training
2026-04-10 | 11:15:13 | ZT4 Time | Chetan | 1
2026-05-04 | 14:13:46 | Thermofisher-Monza (36939) | Chetan | 3 | 1. Support for ST2_PDS - Modifications suggested by Roberto
2026-05-04 | 14:14:10 | Thermofisher-Monza (36940) | Chetan | 4.5 | 1. Support for ST7B- Modifications suggested by Roberto
2026-05-04 | 14:14:31 | ZT4 Time | Chetan | 1 | 1. Support for ST2_PDS. 2. Support for ST7B.